## Sheet1
Capital Project Summary 2020/2021
|  | Paid | Uninvoiced | Estimated | ColC+D+E
Project | 2020-21 | 2020-21 | Work | Cost to | Total | Over/Under
Description | Budget | Invoices | Completed | Complete | Cost | Budget
ELEVATOR - MODERNIZING | 150000 | 136619.08 | 0 | 0 | 136619.08 | -13380.92
BEAM REPLACEMENT | 0 | 9513.37 | 0 | 0 | 9513.37 | 9513.37
SUPPORT POSTS | 0 | 2252.25 | 0 | 0 | 2252.25 | 2252.25
TOTAL MJR PROJECTS | 150000 | 148384.7 | 0 | 0 | 148384.7 | -1615.3
RESERVE ACCT |  | 1ST QTR | 2ND QTR | 3RD QTR | 4TH QTR | YEAR END
|  | SEPT-NOV | DEC - FEB | MAR - MAY | JUNE - AUG | TOTALS
BEGINNING RESERVE BAL - SEPT 1, 2020 |  | 114062.12 |  |  |  | 114062.12
DEPOSITED |  | 10125 | 10125 | 10125 | 10125 | 40500
INTEREST EARNED - EST |  | 41.83 | 24.15 | 36.43 | 22.47 | 124.88
LOAN FUNDS |  |  |  | 75000 | 0 | 75000
LOAN PAYMENTS |  |  |  | -2721.2 | -4082 | -6803.2
SPENT 1ST QTR - EST
SPENT 2ND QTR - EST |  |  | -58302 |  |  | -58302
SPENT 3RD QTR - EST |  |  |  | -86497.7 |  | -86497.7
SPENT 4TH QTR - EST |  |  |  |  | -3585 | -3585
SUB TOTAL |  | 124228.95 | -48152.85 | -4057.47 | 2480.47 | 74499.1
TOTAL RESERVE FUND BALANCE |  | 124228.95 | 76076.1 | 72018.63 | 74499.1 | 74499.1