## CONDO
Item Description | Estimate | Actual | Authorized | Contractor | Target | Target | 2021-2022 |  | Annualized
[Type/Location/Details] | $ | $ | [Board] |  | Start | Finish | Routine | RF Projects | Routine | Notes
A. Beams: (See Specification)(Useful Life 5-20 years) (RFI)
Monitor for rot and paint. See D below. |  |  |  | GBTS |  | Ongoing
Check that railing flanges are sealed.
West Side Beams
Units to Watch Closely: 492 LB (N end), 477 LB, 485 LB & SB,
482 SB, 493 SB (this unit included in CR project Ph1)
479 and 489 LB per Paul 5/22
Paul will confirm 477 (Schedule with future CR)
Kirk Phillips (478) has background in construction and thoughts on CR project
East Side Beams
Phase 4 project authorized 2/22 to start 9/22 | 49915 |  |  | O'Brien | 9/1/22 |  |  |  |  | Was $30,000 in 2017
Phase 1 2014
Phase 2 2015
Phase 3 2016
North end roof valley beam delamination corrected |  | 5332 | plus 1731.24? | OBCo | Complete 2/2022 |  | ? | ?
B. Chimney & Cinder Block :
Seal w/ Thompson/Behr masonary water seal, even years | <$500 |  | X | GBTS |  | Bi-annually
Part of P & G annual inspection and bi-annual recoat |  |  |  | P&G
Track and report needs for mortar & brick work.
Chimney cleaning & Inspection (every five years)( done 2021) |  |  | X | Top Hatter |  |  |  |  | 1000 | clean & inspect fireplaces
C. Concrete:
Pool Deck - Pressure wash annually |  |  | X | GBTS |  | May
Stairs - Pressure wash & paint edge as needed |  |  | X | GBTS |  | Annually
See column pedestals under steel
Repair s.end 2nd floor landing. See Stairways | 9569
D. Decks: (See minimum specifications)(West side are owner responsibility)
West Side - Monitor floor & ceiling. (See Specificiation) |  |  | X |  | Ongoing
Flashing needs repair or replacement 485, 487 | ADVISE | Owner
479 has soft spot | ADVISE | Owner
Flashing repair scheduled Unit 487 NOT COMPLETE |  |  |  | GBTS | 2020/2021 | 2021 ??
Inspect all for railing feet sealant.
East Side - Monitor floor & ceiling. (Useful Life 5-15 years) (RFI) |  |  | X | GBTS | Ongoing
Clean carpets Spring and Fall (2 @ $350)(GBTS) Pressure wash |  | 700 | X | GBTS | June & Oct |  |  |  | 700 | Is this tracked in routine maintenance?
Anticipated repair of soft spots to be accomplished with Phase 4 Beam project | [8 empty] | 500
E. Doors
Monitor for delamination.
Front door: 492 | ADVISE | Owner
E side utilities doors with delamination: 487, 477, 468, 493 | ADVISE | Owner
Replace storm doors per owner needs
Replace and paint main doors per owner needs
F. Electrical: (Useful Life 30 years) (Copper Connections 2015)
Oxidation Removal of Breaker Box | $108-216
New owners being advised that this is desirable but not mandated.
Fire alarm pulls found corroded and required replacement |  | 1750 |  |  |  |  | 1750
Anticipated electrical repiars | [8 empty] | 1000
G. Elevator: (Useful Life 30-50 years) (RFI) Replaced 2021
Regular maintenance |  | 2223 | X | ThyssenKrupp | Ongoing |  |  |  |  | Separate Budget Line
Clean elevator floor daily (see GBTS) |  |  | X | GBTS | Ongoing
Basement entrance way and cab flooring | 2000 |  | X | Carpet Corner | 2021 | Complete |  | 2000
H. Fire Protection (Heat sensors installed 2003, 2 per unit)
Grills
Monitor use of charcoal grills and PROHIBIT |  |  | X | GBTS | Ongoing
Monitor use of gas grills and PROHIBIT BY RENTERS
Under/Toe Kick cabinet heaters - PROHIBIT
Third Floor attic heating and ventilation - Inspect and monitor
I. Hardware: Replace with SS and Plastic
Monitor for corrosion |  |  |  |  | Ongoing
Pool building garage area has nasty grills
Cable connections in plastic boxes, use SS fasteners |  |  |  | GBTS |  | Complete
J. Landscaping Recommendations
Consider landscaping plan for north end. | 4665 |  |  | Manion Landscaping
Committee formed to review proposal & offer recommendation 10/20/21
K. Luggage Carts - Monitor |  |  |  | GBTS | Ongoing
L. Painting: (Useful Life 5-10 years) (RFI unless staged)
Contract for painting in needed areas
Paint west side walls, beams and columns | 16000 | 17000 | X | Anderson | 2021 | Complete | 17000
Anticipated ongoing painting | [8 empty] | 12000
Inspect and recommend next painting project.
M. Parking Garage
Owner adjacent to DH unit is unhappy by door encroachment.
Provide parking for maintenace office.
N. Pool: (Useful Life unknown) (RFI)
Dehumidification Unit (DH) (2009-10)
- Monitor for performance & cold weather operation |  |  |  | Diamond | Ongoing
- Initiate annual routine service contract (2015) |  | $600 x 2 |  | Diamond | Ongoing |  | 1200 |  | 1200
Pool mechanical equipment function under evaluation | 9897 |  | Evaluating | Diamond |  | if necessary |  |  | 3000 | Functionality and need for replacement is being evaluated
Fans running (to exhaust humidity) and room heated but no dehumidification
Monitor pool lining | Need new quote |  |  |  | 2017
- New concrete base (2 feet thick)
Normal pool check: chemicals, operations, cleaning |  |  |  | GBTS
Damage near door by dilivery truck. Remedy in progress. Status? | By driver's company |  |  | OB&Co | 10/21 |  |  |  |  | Insurance paid but work not done. No roofers
Pool cover and reel replacement | 400 |  | X | GBTS | 8/21 |  | 400 |  |  | Ordered
O. Plumbing: RFI (W, S, Septic Useful Life 25-50 years)
Water System: Monitor (Replaced with PEX 2008) |  |  |  | Owners & GBTS
Septic Tank Monitor (Replaced with 3-HDPE 2012)
Septic Tank Maintenance (pump per EMS inspection, 2022) | 5500 | [5 empty] | 5500 |  | 1300 | 6500
Interior Drains (ongoing clogging issues) Monitor |  |  |  | GBTS/Osbourne |  |  |  |  | 1000
Access cleaning from garage covers
-Annual Inspection (initiated 9/2021) |  | 440 |  |  |  |  | 440 |  | 440
Unit Issues:
Limit use of garbage disposals by REMOVAL | $20/unit |  | X | GBTS | 37591 | Ongoing
Does Units 487 still have a disposal? | ADVISE | Owner |  |  | YES
Tub & shower drain replacement: Owner Responsibility plus | Owner |  |  | Send Letter on Responsibilty
repair of adjacent units if failure
Unit 491 problem? Temporary fix. Paul? | ADVISE | Owner
Inspect and replace water heaters >15 years | ADVISE | Owner |  | Send Letter on Responsibilty
Caution owners to turn refrigerator supply off when not in regular use
Drains are old andclogging is a problem. Report immediately.
P. Railings:
Monitor Wasser paint for durability and need to re-galvanize |  |  | X | GBTS | Ongoing
Parking lot stairway rails are showing some deterioration
Replace all eight: galv $3640, ss $4210, alum $3764 ($470/rail) | 3764 |  |  | Coastal R & M (2007)
Paint including base plates
See CR project
R. Roofing: (Useful Life 15 years from 2014) (RFI)
(Valley membrane may be from 2000)
Unit 490-481-472 stack is under repair due to scupper/valley damage |  | 1472 |  | O'Brien and P&G | ASAP
Units 492 and 491 have living room leaks |  |  |  | P & G Roofing | ASAP
Units 486 and 478 have west exterior closet leaks |  |  |  | P & G Roofing | ASAP
Inspect roof anchor brackets for paint or replacement. See steel column item.
Downspout on south end is compromised. O'Brien will evaluate repair options
SE scupper needs to be cleared and or repaired
Roof Access Hatch | 6000 |  | X | Pacific Coast | 6/22
Valleys inspected with minor repairs 2/17/22 and recommendation
is that replacement is necessary. Estimates requested. | 138000 | ???
S. Siding:
Anticipated siding repair | [8 empty] | 1000
Note deck build-up & siding issue
Unit 475 has wind driven rain getting into his west side closet. O'brien will offer repair options. Did this get fixed. Leonard (Len) Kaufman
Unit 477 has dry rot in T1-11 behind downspout. CR project side job.
Two units 490 and 481 had exterior and interior water damage due to damaged scupper.
Exterior siding replaced (interior unclear) |  |  |  |  | 2/2022
Unit 493 north side has rotted area.
T. Signs: Monitor for appearance
U. Stairways:
Paint leading edge of tred as needed.
V. Steel Columns & Pedestals: (Useful Life 5- 50 years) (RFI)
Proposed to replace the column and 6 railing segments and six | 50000 |  | Approved | Sopko | 2021 |  |  | 50000
beams (as required) on the south end unit stack on a time and materials
basis. This will allow contractor to make a more accurate bid for
the balance of the units and financial planning.
Kirk Phillips (478) has background in construction and thoughts on CR project
W. Swallow & Bee Nesting - Monitor and remove before hatch.
X. TV Upgrade & Wiring (Is this a maintenance item?)
System is part of the GBTS infrastucture
Cable inside the building is PV
New cables (coax & cat5or6) from maintenance to north stack (6)
with access boxes to the remaining stacks. This is complete |  | 4700 |  | Air Wave |  | Done |  | 4700
and Paul reports no complaints 4/22.
No funding for additional stacks at this time. Monitor for performance.
Balance of project would cost $20,000 - $4,700 = $15.300 | 15300
Four 6 stack and one 3 stack.
Reserve Committee (Review initiated 2022)
Consider whether the above Maintenance Schedule is adequately inclusive and financially sound.
Consider whether a certified reserve study is required or desirable.
Committee Members: Jim Andrews, Jim Thomas, Scott Samuelson, …
CURRENT BUDGET ITEMS IDENTIFIED | [6 empty] | 26290 | 56700 | 23140 | If column project is approved
GBTS TIME AND MATERIALS (2020-2021) | [6 empty] | 22066 |  | 22066
[7 empty] | 48356 | 56700 | 45206
NOTES:
1. Pacific View was completed in August 1967.
2. GBTS shall contact a local contractor if repair needs exceed time or skills of staff.
3. RFI = Reserve Fund Item

## Layout
PACIFIC VIEW LAYOUT
2021 - 2022
ELEVATOR
ANDREWS | ICDC - SPRINGER | THOMAS | POWELL | CLJ Properties | CHISHOLM | R&R | HAUGHTON | WEIL
Jim & Peggy | Mary Kay | Jim | Gary & Jane | Charley Jones | Tom & Alice | Rosenthal, Sam | Douglas / Diane | Jay & Karen
Tom & Lauren | Charles & Christie | Teresa |  | Marc Weaver |  | Rosenthal, Gabe
| Patricia |  |  |  | diy deck repair
guest br wet
see roofer
493 | 492 | 491 | 490 | 489 | 488 | 487 | 486 | 485
WILKINS | SEIBERT | SAMUELSON | JOHNSON | MOORE | WILHELM | PHILLIPS | COOPER | BEERLI
Bill & Dolly | John & Barbara | Scott & Margy | Joe | Carol | Lillian & Bob | Kirk & Shery | Jack & Mary Kay | Margit
maybe issue f above
| DUNBAR |  | AUBLE |  | bad deck | selling
| William & Candy |  | Mary Ellen
484 | 483 | 482 | 481 | 480 | 479 | 478 | 477 | 476
KAUFFMAN | BERTELLOTTI | JOHNSTON | MILLSAP | MENDEZ | BAILEY | FARRELL | JOHNSON | TOWNSEND
Len & Sheri | Richard & Leslie | Roger | Orville & Eileen | Jean & Gabriel | Nancy | Mark & Elizabeth | Peter & Janet | David
|  | KAHL | [5 empty] | USHER
|  | Barbara | [5 empty] | Sharon
475 | 474 | 473 | 472 | 471 | 470 | 469 | 468 | 467
ELEVATOR