## CONDO
Item Description | Estimate | Actual | Authorized | Contractor | Target | Target | 2021-2022 |  | Annualized
[Type/Location/Details] | $ | $ | [Board] |  | Start | Finish | Routine | RF Projects | Routine | Notes
A. Beams: (See Specification)(Useful Life 5-20 years) (RFI)
Monitor for rot and paint. See D below. |  |  |  | GBTS |  | Ongoing
Check that railing flanges are sealed.
West Side Beams
Anticipated beam replacement | [7 empty] | See V. below
Unit 474 LB replaced | 10000 | 9513 |  | O'Brien | 2020/2021 | Complete 4/21
Unit to Watch Closely: 492 LB (N end), 477 LB, 485 LB & SB,
482 SB, 493 SB (this unit included in CR project Ph1)
Paul will confirm 477 (Schedule with future CR)
Kirk Phillips (478) has background in construction and thoughts on CR project
East Side Beams
Phase 4 Repairs 2018-19 (Estimate date 7/4/17) | 29879.2 |  |  | O'Brien | Not Urgent
B. Chimney & Cinder Block :
Seal w/ Thompson/Behr masonary water seal, even years | <$500 |  | X | GBTS |  | Bi-annually
Part of P & G annual inspection and bi-annual recoat |  |  |  | P&G
Track and report needs for mortar & brick work.
Chimney cleaning & Inspection (every five years)( done 2021) | 2856 | 2618 | X | Top Hatter | 2020/21 | Complete 6/21 |  |  | 1000 | clean & inspect fireplaces
Repair work is additional |  | 2375 | [7 empty] | cleaning and seal 5 chimneys
C. Concrete:
Pool Deck - Pressure wash annually |  |  | X | GBTS |  | May
Stairs - Pressure wash & paint edge as needed |  |  | X | GBTS |  | Annually
See column pedestals under steel
Repair s.end 2nd floor landing. See Stairways | 9569
D. Decks: (See minimum specifications)(West side are owner responsibility)
West Side - Monitor floor & ceiling. (See Specificiation) |  |  | X |  | Ongoing
Flashing needs repair or replacement 485, 487 | ADVISE | Owner
479 has soft spots | ADVISE | Owner
Flashing repair scheduled Unit 487 NOT COMPLETE |  |  |  | GBTS | 2020/2021 | 2021 ??
Inspect all for railing feet sealant.
East Side - Monitor floor & ceiling. (Useful Life 5-15 years) (RFI) |  |  | X | GBTS | Ongoing
Clean carpets Spring and Fall (2 @ $350)(GBTS) Pressure wash |  | 700 | X | GBTS | June & Oct |  |  |  | 700 | Is this tracked in routine maintenance?
Anticipated repair of soft spots | [8 empty] | 500
E. Doors
Monitor for delamination.
Front door: 492 | ADVISE | Owner
E side utilities doors with delamination: 487, 477, 468, 493 | ADVISE | Owner
Replace storm doors per owner needs
Replace and paint main doors per owner needs
F. Electrical: (Useful Life 30 years)
Oxidation Removal of Breaker Box | $108-216
New owners being advised that this is desirable but not mandated.
Fire alarm pulls found corroded and required replacement |  | 1750 |  |  |  |  | 1750
Anticipated electrical repiars | [8 empty] | 1000
G. Elevator: (Useful Life Unknown) (RFI)
Regular maintenance |  | 2223 | X | ThyssenKrupp | Ongoing |  |  |  |  | Separate Budget Line
Clean elevator floor daily (see GBTS) |  |  | X | GBTS | Ongoing
Full Repair and Modernization | $150-170K | 136619 | X | ThyssenK | 2020 | Complete
Basement entrance way and cab flooring | 2000 |  | X | Carpet Corner | 2021 | Complete |  | 2000
H. Grills
Monitor use of charcoal grills and PROHIBIT |  |  | X | GBTS | Ongoing
Monitor use of gas grills and prohibit by renters
I. Hardware: Replace with SS and Plastic
Monitor for corrosion |  |  |  |  | Ongoing
Pool building garage area has nasty grills
Cable connections in plastic boxes, use SS fasteners |  |  |  | GBTS |  | Complete
J. Landscaping Recommendations
Study whether sprinkler systems offset by GBTS labor. | GBTS |  | Not at this time
Consider landscaping plan for north end. | 4665 |  |  | Manion Landscaping
K. Luggage Carts - Monitor |  |  |  | GBTS | Ongoing
L. Paint: (Useful Life 5-10 years) (RFI unless staged)
Contract for painting in needed areas
Paint west side walls, beams and columns | 16000 | 17000 | X | Anderson | in progress | 10/21 | 17000
Anticipated ongoing painting | [8 empty] | 12000
M. Parking Garage
Owner adjacent to DH unit is unhappy by door encroachment.
Provide parking for maintenace office.
N. Pool: (Useful Life unknown) (RFI)
Pool room heating & dehumidification modernization
Dehumidification Unit (DH)
- Monitor for performance & cold weather operation |  |  |  | Diamond | Ongoing
- Initiate annual routine service contract (2015) |  | $600 x 2 |  | Diamond | Ongoing |  | 1200 |  | 1200
Pool mechanical equipment function under evaluation | 7200 |  | Evaluating |  |  | if necessary |  |  | 3000 | Functionality and need for replacement is being evaluated
Fans running (to exhaust humidity) and room heated but no dehumidification
Monitor pool lining | Need new quote |  |  |  | 2017
- New concrete base (2 feet thick)
Normal pool check: chemicals, operations, cleaning |  |  |  | GBTS
Damage near door by dilivery truck. Remedy in progress | By driver's company |  |  | OB&Co | 10/21 |  |  |  |  | Insurance paid but work not done. No roofers
Pool cover and reel replacement | 400 |  | X | GBTS | 8/21 |  | 400 |  |  | Ordered
O. Plumbing: RFI (W, S, Septic Useful Life 25-50 years)
Water System: Monitor for flow & corrosion |  |  |  | Owners & GBTS
Septic Tank Maintenance (pump per EMS inspection, 2022) | 5500 | [5 empty] | 5500 |  | 1300 | 6500
-Annual Inspection (initiated 9/2021) |  | 440 |  |  |  |  | 440 |  | 440
Interior building drain lines. Monitor and maintain. Ongoing |  |  |  | GBTS/Osbourne
Site drainage - Divert from adjacent property by bubble drain | 800 | 1175 | X | Cleansweep | 2021 |  | 1175
Unit Issues:
Limit use of garbage disposals by REMOVAL | $20/unit |  | X | GBTS | 37591 | Ongoing
Does Units 487 still have a disposal? | ADVISE | Owner |  |  | YES
Tub & shower drain replacement: Owner Responsibility plus | Owner |  |  | Send Letter on Responsibilty
repair of adjacent units if failure
Unit 491 problem? Temporary fix. Paul? | ADVISE | Owner
Inspect and replace water heaters >15 years | ADVISE | Owner |  | Send Letter on Responsibilty
Drains are old and backup are a problem. Rport immediately.
Anticipated building sewer cleaning | [8 empty] | 1000
P. Railings:
Monitor Wasser paint for durability and need to re-galvanize |  |  | X | GBTS | Ongoing
Parking lot stairway rails are showing some deterioration
Replace all eight: galv $3640, ss $4210, alum $3764 ($470/rail) | 3764 |  |  | Coastal R & M (2007)
Paint including base plates
Solicit proposals to bring up to Code
Polycarbonate panels may be the best solution
See railing feet sealing under decks
See CR project
R. Roofing: (Useful Life 15 years from 2014) (RFI)
Expedite repair of any reported leaks. See Note 2 |  |  | X | P & G Roofing | Immediate | Ongoing
Monitor roof valley downspouts |  |  | X | P & G Roofing | Ongoing
A number of downspouts are leaking at joints or at exit to
roof scuppers. Ask roofer to correct upper work. See if GBTS
wants to tackle lower work?
Inspect roof anchor brackets for paint or replacement. See steel column item.
Downspout on south end is compromised. O'Brien will evaluate repair options
SE scupper needs to be cleared and or repaired |  |  |  | P & G Roofing
Valleys are older than new roof and need watching
S. Siding:
Anticipated siding repair | [8 empty] | 1000
See G. above for painting.
Monitor for condition and advise.
Note deck build-up & siding issue
Unit 475 has wind driven rain getting into his west side close. O'brien will offer repair options. Did this get fixed. Leonard (Len) Coffman
Unit 477 has dry rot in T1-11 behind downspout. CR project side job.
T. Signs: Monitor for appearance
U. Stairways:
Paint leading edge of tred per B above (or as needed).
Second floor landing is slanting repair. | 9569 | 11791 | OB&Co |  | 2020 | Complete 8/25 |  |  |  | Is this normal maintenance?
New column required (change order at cost), $2,222
Replace 2 treds |  | 813 | Sopko |  |  | Complete 1/21
V. Steel Columns & Pedestals: (Useful Life 5- 50 years) (RFI)
Proposed to replace the column and 6 railing segments and six | 50000 |  | RECOMMENDED | Sopko | 2021 |  |  | 50000
beams (as required) on the south end unit stack on a time and materials
basis. This will allow contractor to make a more accurate bid for
the balance of the units and financial planning.
Kirk Phillips (478) has background in construction and thoughts on CR project
W. Swallow & Bee Nesting - Monitor and remove before hatch.
X. TV Upgrade & Wiring (Is this a maintenance item?)
System is part of the GBTS infrastucture
Cable inside the building is PV
Building is to get new cables (coax & cat5or6) to maintenance
that could allow boosters in north 6 stack if required. | 3500 |  |  | Air Wave |  |  |  | 3500
Pixilation Reports: Jay Weil 485, Shery Phillips 478
NOTES:
1. Pacific View was completed in August 1967.
2. GBTS shall contact a local contractor if repair needs exceed time or skills of staff.
3. RFI = Reserve Fund Item
CURRENT BUDGET ITEMS IDENTIFIED | [6 empty] | 27465 | 55500 | 23140 | If column project is approved
GBTS TIME AND MATERIALS (2020-2021) | [6 empty] | 22066 |  | 22066
[7 empty] | 49531 | 55500 | 45206